Somaliland Shelter Cluster coordination meeting minutes

Thursday the 5th of November, 2015.

At MRR&R Office, Hargeisa

Participants;-

- Veronic			UNHCR

- Mohamed Jama Hashi		NRC

- Hassan Warsame		UNOCHA

- Ismail				DRC

- Abdi Ali			MRR&R

- Suhur Muse			UNHABITAT

| Agenda | Discussion points in summery/action points |
| --- | --- |
| Response to the drought affected IDPs in the coastal areas of Awdal and Maroodi jeh regions. | UNICIEF;-Abdilahi Sh. Who is supposed to join us attended another important meeting as he said. However, he told us that they have up to 1500 kits (Plastic sheet & Blankets) for droughts. UNHCR;- Will provide NFIs to the drought affected IDPs through cluster members on the basis of the IDPs assessment report. Moreover, UNHCR will provide NFIs to newly displaced people due El-Nino in Bulahar district (Shacaable village) on the basis of OCHA’s official information on the matter. NRC;- Will distribute dignity kits along with NFI distribution; shelter cluster shall lead the group to distribute the NFIs (the distribution group consists of NRC, DRC, UNHABITAT and MoRRR); NRC will also participate distribution exercises in the field. UNHABITAT;- Will deploy staff members and vehicle to the distribution sites, also contribute logistics arrangements (NFI transportations). DRC;- confirmed their participation , staff members from DRC to join distribution team. Distribution Team;-It was agreed that with the lead of NRC, staff members from NRC, UNHABITAT, DRC &MRR&R to form distribution team. Head of these agencies is asked to send the names of the individuals participating this exercise to the cluster focal point. Agreed action points;- Cluster coordinator to contact FCA on possible contribution to this response. Appointed distribution team members to be trained by FCA. UNHCR upon the receipt of this report will disseminate the number of NFI kits that UNHCR has for this drought response. NRC, UNHABITAT, DRC in this meeting to meet again on Sunday, November8, 2015. 10;00am at MRR&R . UNHABITAT, NRC, DRC & MRR&R to submit the names of the individuals participating this exercise . |
| Displacements in Eal-shiek village as a result of a Chapala cyclone | OCHA has made a contact to a chairman of Bullahar who confirmed that 45 HHs (400 people) were displaced in Eeel Sheik area of Bulahar district due to sea water flooding resulted by the Chapala cyclone which hit Oman and Yemen. . the displaced people who lives on the sea shore saw their homes flood when the sea level rose and flooded their homes, causing them to flee for their lives. According to the information provided by the chairman of Bullahar SRCS distributed 180 blankets and mats at the onset of the incedent. immediate needs include NFIs, food etc. Action point;- UNHCR upon the receipt of this minutes respond to the needs identified here in above . |
| updates on other Cluster responses | UNHCR has just distributed NFI kits to 618 house hols in Koosar IDPs settlement in Burao through DRC, these families were amongst over a 900 HH who lost their shelters as a result of a stormy rain which hit Burao some time in September,2015. |

Mohamed Jama Hashi

Shelter Cluster Coordinator, Somaliland