## 2017 HRP Target
| Rest of Iraq | KRI | Mosul | Total (Ind.) | Total (HH.)
# People targeted | 1130591 | 546892 | 648858 | 2326341 | 387723.5
# of partners with approved projects in the HRP | 29 | 13 | 25
Financial requirements | 73879938 | 41918452 | 59515318 | 175313708
Cluster coordinator name and email address: | Richard Evans
coord.iraq@sheltercluster.org
Cluster co-coordinator name and email address: | Michael Gloeckle
coord2.iraq@sheltercluster.org
Target per indicators as in 2017 HRP
| NFI (ind.) | Shelter (Ind.) | Total
Objective 1 / 1st line response | 1190204 | 344258
Objective 2 / 2nd line response | 100246 | 256530
12234
382978
Objective 3 / Full response |  | 41534
| 1290450 | 1037534 | 2327984
| 215075 | 172922.3333 | 387997.3333
Note on B16: Distribution of NFI kits
Note on C16: Emergency shelter
Note on B17: NFI replenishment
Note on C17: Tents replacement
Note on C18: Shelter upgrade with concrete slabs
Note on C19: Basic shelter repair / upgrade
Note on C20: repair of heavily damaged houses

## Jan.17
2017-01-01 |  |  |  | Cluster response Jan.17 |  | First Line |  | Second Line |  | Full Response
Governerate | Admin 1 Code | PEOPLE IN NEED | Target | NFI | Shelter | Emergency NFI | Emergency Shelter | NFI Replenishment | Shelter Upgrade/Repair | NFI3 | Shelter and housing options
Anbar | IQ-G01 | 886545.3496 | 490242.116 | 18858 | 1902 | 18858 | 642 | 0 | 1260 | 0 | 0
Babylon | IQ-G06 | 18256.1041 | 10095.266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Baghdad | IQ-G07 | 163558.6023 | 90444.6854 | 2100 | 0 | 2100 | 0 | 0 | 0 | 0 | 0
Basrah | IQ-G02 | 2446.4634 | 1352.8461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dahuk | IQ-G08 | 275356.378 | 262285.4915 | 24 | 7500 | 24 | 0 | 0 | 7500 | 0 | 0
Diyala | IQ-G10 | 196589.4267 | 108710.0807 | 5064 | 0 | 5064 | 0 | 0 | 0 | 0 | 0
Erbil | IQ-G11 | 233090.3732 | 222025.8108 | 3540 | 0 | 3540 | 0 | 0 | 0 | 0 | 0
Kerbala | IQ-G12 | 25547.226 | 14127.1127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kirkuk | IQ-G13 | 301949.0932 | 166971.901 | 8622 | 0 | 8622 | 0 | 0 | 0 | 0 | 0
Missan | IQ-G14 | 1992.2148 | 1101.6556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Muthanna | IQ-G03 | 1255.951 | 694.5162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Najaf | IQ-G17 | 25088.5144 | 13873.4543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ninewa | IQ-G15 | 1264312.6901 | 648858 | 214278 | 2586 | 214278 | 2520 | 0 | 66 | 0 | 0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845 | 23676 | 21300 | 23676 | 21240 | 0 | 60 | 0 | 0
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wassit | IQ-G16 | 8074.2609 | 4464.9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Individuals |  | 3883000 | 2326341 | 276162 | 33288 | 276162 | 24402 | 0 | 8886 | 0 | 0
Total Households |  | 647166.6667 | 387723.5 | 46027 | 5548 | 46027 | 4067 | 0 | 1481 | 0 | 0
|  |  |  | 11.87% | 1.431%
KR-I
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Dahuk | IQ-G08 | 275356.378 | 262285.4915
Erbil | IQ-G11 | 233090.3732 | 222025.8108
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977
Total Individuals |  | 574146.1316 | 546892
Total Households |  | 95691.0219 | 91148.6667
Rest of Iraq
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Anbar | IQ-G01 | 886545.3496 | 490242.116
Babylon | IQ-G06 | 18256.1041 | 10095.266
Baghdad | IQ-G07 | 163558.6023 | 90444.6854
Basrah | IQ-G02 | 2446.4634 | 1352.8461
0
Diyala | IQ-G10 | 196589.4267 | 108710.0807
0
Kerbala | IQ-G12 | 25547.226 | 14127.1127
Kirkuk | IQ-G13 | 301949.0932 | 166971.901
Missan | IQ-G14 | 1992.2148 | 1101.6556
Muthanna | IQ-G03 | 1255.951 | 694.5162
Najaf | IQ-G17 | 25088.5144 | 13873.4543
0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845
0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694
Wassit | IQ-G16 | 8074.2609 | 4464.9072
Total Individuals |  | 2044541.1783 | 1130591
Total Households |  | 340756.8631 | 188431.8333
Mosul / Ninewa
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Ninewa | IQ-G15 | 1264312.6901 | 648858
Total Individuals |  | 1264312.6901 | 648858
Total Households |  | 210718.7817 | 108143

## Feb.17
2017-02-01 |  |  |  | Cluster response Feb.17 |  | First Line |  | Second Line |  | Full Response
Governerate | Admin 1 Code | PEOPLE IN NEED | Target | NFI | Shelter | Emergency NFI | Emergency Shelter | NFI Replenishment | Shelter Upgrade/Repair | NFI3 | Shelter and housing options
Anbar | IQ-G01 | 886545.3496 | 490242.116 | 1764 | 3240 | 1764 | 0 | 0 | 3240 | 0 | 0
Babylon | IQ-G06 | 18256.1041 | 10095.266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Baghdad | IQ-G07 | 163558.6023 | 90444.6854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Basrah | IQ-G02 | 2446.4634 | 1352.8461 | 144 | 0 | 144 | 0 | 0 | 0 | 0 | 0
Dahuk | IQ-G08 | 275356.378 | 262285.4915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Diyala | IQ-G10 | 196589.4267 | 108710.0807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Erbil | IQ-G11 | 233090.3732 | 222025.8108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kerbala | IQ-G12 | 25547.226 | 14127.1127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kirkuk | IQ-G13 | 301949.0932 | 166971.901 | 5586 | 72870 | 5586 | 63708 | 0 | 9162 | 0 | 0
Missan | IQ-G14 | 1992.2148 | 1101.6556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Muthanna | IQ-G03 | 1255.951 | 694.5162 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0
Najaf | IQ-G17 | 25088.5144 | 13873.4543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ninewa | IQ-G15 | 1264312.6901 | 648858 | 56640 | 70848 | 56640 | 61692 | 0 | 9156 | 0 | 0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049 | 60 | 0 | 60 | 0 | 0 | 0 | 0 | 0
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845 | 12492 | 39774 | 12492 | 14934 | 0 | 24840 | 0 | 0
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wassit | IQ-G16 | 8074.2609 | 4464.9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Individuals |  | 3883000 | 2326341 | 76698 | 186732 | 76698 | 140334 | 0 | 46398 | 0 | 0
Total Households |  | 647166.6667 | 387723.5 | 12783 | 31122 | 12783 | 23389 | 0 | 7733 | 0 | 0
|  |  |  | 3.297% | 8.027%
KR-I
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Dahuk | IQ-G08 | 275356.378 | 262285.4915
Erbil | IQ-G11 | 233090.3732 | 222025.8108
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977
Total Individuals |  | 574146.1316 | 546892
Total Households |  | 95691.0219 | 91148.6667
Rest of Iraq
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Anbar | IQ-G01 | 886545.3496 | 490242.116
Babylon | IQ-G06 | 18256.1041 | 10095.266
Baghdad | IQ-G07 | 163558.6023 | 90444.6854
Basrah | IQ-G02 | 2446.4634 | 1352.8461
0
Diyala | IQ-G10 | 196589.4267 | 108710.0807
0
Kerbala | IQ-G12 | 25547.226 | 14127.1127
Kirkuk | IQ-G13 | 301949.0932 | 166971.901
Missan | IQ-G14 | 1992.2148 | 1101.6556
Muthanna | IQ-G03 | 1255.951 | 694.5162
Najaf | IQ-G17 | 25088.5144 | 13873.4543
0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845
0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694
Wassit | IQ-G16 | 8074.2609 | 4464.9072
Total Individuals |  | 2044541.1783 | 1130591
Total Households |  | 340756.8631 | 188431.8333
Mosul / Ninewa
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Ninewa | IQ-G15 | 1264312.6901 | 648858
Total Individuals |  | 1264312.6901 | 648858
Total Households |  | 210718.7817 | 108143

## Mar.17
2017-03-01 |  |  |  | Cluster response Mar.17 |  | First Line |  | Second Line |  | Full Response
Governerate | Admin 1 Code | PEOPLE IN NEED | Target | NFI | Shelter | Emergency NFI | Emergency Shelter | NFI Replenishment | Shelter Upgrade/Repair | NFI3 | Shelter and housing options
Anbar | IQ-G01 | 886545.3496 | 490242.116 | 8868 | 0 | 8868 | 0 | 0 | 0 | 0 | 0
Babylon | IQ-G06 | 18256.1041 | 10095.266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Baghdad | IQ-G07 | 163558.6023 | 90444.6854 | 2238 | 1998 | 2238 | 0 | 0 | 1788 | 0 | 210
Basrah | IQ-G02 | 2446.4634 | 1352.8461 | 156 | 0 | 156 | 0 | 0 | 0 | 0 | 0
Dahuk | IQ-G08 | 275356.378 | 262285.4915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Diyala | IQ-G10 | 196589.4267 | 108710.0807 | 96 | 300 | 96 | 0 | 0 | 0 | 0 | 300
Erbil | IQ-G11 | 233090.3732 | 222025.8108 | 36012 | 0 | 36012 | 0 | 0 | 0 | 0 | 0
Kerbala | IQ-G12 | 25547.226 | 14127.1127 | 0 | 204 | 0 | 0 | 0 | 0 | 0 | 204
Kirkuk | IQ-G13 | 301949.0932 | 166971.901 | 20292 | 25368 | 20292 | 150 | 0 | 25104 | 0 | 114
Missan | IQ-G14 | 1992.2148 | 1101.6556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Muthanna | IQ-G03 | 1255.951 | 694.5162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Najaf | IQ-G17 | 25088.5144 | 13873.4543 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 240
Ninewa | IQ-G15 | 1264312.6901 | 648858 | 200766 | 86610 | 200766 | 70260 | 0 | 16350 | 0 | 0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845 | 39300 | 1662 | 39300 | 600 | 0 | 0 | 0 | 1062
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977 | 42 | 36 | 42 | 0 | 0 | 36 | 0 | 0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694 | 138 | 0 | 138 | 0 | 0 | 0 | 0 | 0
Wassit | IQ-G16 | 8074.2609 | 4464.9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Individuals |  | 3883000 | 2326341 | 307908 | 116418 | 307908 | 71010 | 0 | 43278 | 0 | 2130
Total Households |  | 647166.6667 | 387723.5 | 51318 | 19403 | 51318 | 11835 | 0 | 7213 | 0 | 355
|  |  |  | 13.24% | 5.004%
KR-I
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Dahuk | IQ-G08 | 275356.378 | 262285.4915
Erbil | IQ-G11 | 233090.3732 | 222025.8108
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977
Total Individuals |  | 574146.1316 | 546892
Total Households |  | 95691.0219 | 91148.6667
Rest of Iraq
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Anbar | IQ-G01 | 886545.3496 | 490242.116
Babylon | IQ-G06 | 18256.1041 | 10095.266
Baghdad | IQ-G07 | 163558.6023 | 90444.6854
Basrah | IQ-G02 | 2446.4634 | 1352.8461
0
Diyala | IQ-G10 | 196589.4267 | 108710.0807
0
Kerbala | IQ-G12 | 25547.226 | 14127.1127
Kirkuk | IQ-G13 | 301949.0932 | 166971.901
Missan | IQ-G14 | 1992.2148 | 1101.6556
Muthanna | IQ-G03 | 1255.951 | 694.5162
Najaf | IQ-G17 | 25088.5144 | 13873.4543
0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845
0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694
Wassit | IQ-G16 | 8074.2609 | 4464.9072
Total Individuals |  | 2044541.1783 | 1130591
Total Households |  | 340756.8631 | 188431.8333
Mosul / Ninewa
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Ninewa | IQ-G15 | 1264312.6901 | 648858
Total Individuals |  | 1264312.6901 | 648858
Total Households |  | 210718.7817 | 108143

## Apr.17
2017-04-01 |  |  |  | Cluster response Apr.17 |  | First Line |  | Second Line |  | Full Response
Governerate | Admin 1 Code | PEOPLE IN NEED | Target | NFI | Shelter | Emergency NFI | Emergency Shelter | NFI Replenishment | Shelter Upgrade/Repair | NFI3 | Shelter and housing options
Anbar | IQ-G01 | 886545.3496 | 490242.116 | 0 | 2076 | 0 | 2058 | 0 | 18 | 0 | 0
Babylon | IQ-G06 | 18256.1041 | 10095.266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Baghdad | IQ-G07 | 163558.6023 | 90444.6854 | 600 | 0 | 600 | 0 | 0 | 0 | 0 | 0
Basrah | IQ-G02 | 2446.4634 | 1352.8461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dahuk | IQ-G08 | 275356.378 | 262285.4915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Diyala | IQ-G10 | 196589.4267 | 108710.0807 | 216 | 18 | 216 | 0 | 0 | 18 | 0 | 0
Erbil | IQ-G11 | 233090.3732 | 222025.8108 | 9396 | 0 | 798 | 0 | 8598 | 0 | 0 | 0
Kerbala | IQ-G12 | 25547.226 | 14127.1127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kirkuk | IQ-G13 | 301949.0932 | 166971.901 | 5706 | 1602 | 5706 | 6 | 0 | 1596 | 0 | 0
Missan | IQ-G14 | 1992.2148 | 1101.6556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Muthanna | IQ-G03 | 1255.951 | 694.5162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Najaf | IQ-G17 | 25088.5144 | 13873.4543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ninewa | IQ-G15 | 1264312.6901 | 648858 | 244206 | 98892 | 244206 | 97662 | 0 | 1230 | 0 | 0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845 | 10074 | 9714 | 10074 | 6714 | 0 | 3000 | 0 | 0
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977 | 12 | 36 | 12 | 0 | 0 | 36 | 0 | 0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Wassit | IQ-G16 | 8074.2609 | 4464.9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Individuals |  | 3883000 | 2326341 | 270210 | 112338 | 261612 | 106440 | 8598 | 5898 | 0 | 0
Total Households |  | 647166.6667 | 387723.5 | 45035 | 18723 | 43602 | 17740 | 1433 | 983 | 0 | 0
|  |  |  | 11.62% | 4.829%
KR-I
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Dahuk | IQ-G08 | 275356.378 | 262285.4915
Erbil | IQ-G11 | 233090.3732 | 222025.8108
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977
Total Individuals |  | 574146.1316 | 546892
Total Households |  | 95691.0219 | 91148.6667
Rest of Iraq
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Anbar | IQ-G01 | 886545.3496 | 490242.116
Babylon | IQ-G06 | 18256.1041 | 10095.266
Baghdad | IQ-G07 | 163558.6023 | 90444.6854
Basrah | IQ-G02 | 2446.4634 | 1352.8461
0
Diyala | IQ-G10 | 196589.4267 | 108710.0807
0
Kerbala | IQ-G12 | 25547.226 | 14127.1127
Kirkuk | IQ-G13 | 301949.0932 | 166971.901
Missan | IQ-G14 | 1992.2148 | 1101.6556
Muthanna | IQ-G03 | 1255.951 | 694.5162
Najaf | IQ-G17 | 25088.5144 | 13873.4543
0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845
0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694
Wassit | IQ-G16 | 8074.2609 | 4464.9072
Total Individuals |  | 2044541.1783 | 1130591
Total Households |  | 340756.8631 | 188431.8333
Mosul / Ninewa
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Ninewa | IQ-G15 | 1264312.6901 | 648858
Total Individuals |  | 1264312.6901 | 648858
Total Households |  | 210718.7817 | 108143

## May.17
2017-05-01 |  |  |  | Cluster response Mai.17 |  | First Line |  | Second Line |  | Full Response
Governerate | Admin 1 Code | PEOPLE IN NEED | Target | NFI | Shelter | Emergency NFI | Emergency Shelter | NFI Replenishment | Shelter Upgrade/Repair | NFI3 | Shelter and housing options
Anbar | IQ-G01 | 886545.3496 | 490242.116 | 1848 | 642 | 1848 | 480 | 0 | 6 | 0 | 156
Babylon | IQ-G06 | 18256.1041 | 10095.266 | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 210
Baghdad | IQ-G07 | 163558.6023 | 90444.6854 | 0 | 1416 | 0 | 0 | 0 | 0 | 0 | 1416
Basrah | IQ-G02 | 2446.4634 | 1352.8461 | 420 | 0 | 420 | 0 | 0 | 0 | 0 | 0
Dahuk | IQ-G08 | 275356.378 | 262285.4915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Diyala | IQ-G10 | 196589.4267 | 108710.0807 | 282 | 3078 | 282 | 0 | 0 | 3078 | 0 | 0
Erbil | IQ-G11 | 233090.3732 | 222025.8108 | 3282 | 840 | 0 | 0 | 3282 | 0 | 0 | 840
Kerbala | IQ-G12 | 25547.226 | 14127.1127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kirkuk | IQ-G13 | 301949.0932 | 166971.901 | 4950 | 3114 | 4950 | 576 | 0 | 2538 | 0 | 0
Missan | IQ-G14 | 1992.2148 | 1101.6556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Muthanna | IQ-G03 | 1255.951 | 694.5162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Najaf | IQ-G17 | 25088.5144 | 13873.4543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ninewa | IQ-G15 | 1264312.6901 | 648858 | 99150 | 32742 | 99150 | 27042 | 0 | 5700 | 0 | 0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049 | 240 | 0 | 240 | 0 | 0 | 0 | 0 | 0
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845 | 10944 | 2892 | 10944 | 960 | 0 | 1230 | 0 | 702
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977 | 108 | 2178 | 108 | 6 | 0 | 2172 | 0 | 0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694 | 180 | 0 | 180 | 0 | 0 | 0 | 0 | 0
Wassit | IQ-G16 | 8074.2609 | 4464.9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Individuals |  | 3883000 | 2326341 | 121404 | 47112 | 118122 | 29064 | 3282 | 14724 | 0 | 3324
Total Households |  | 647166.6667 | 387723.5 | 20234 | 7852 | 19687 | 4844 | 547 | 2454 | 0 | 554
|  |  |  | 5.219% | 2.025%
KR-I
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Dahuk | IQ-G08 | 275356.378 | 262285.4915
Erbil | IQ-G11 | 233090.3732 | 222025.8108
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977
Total Individuals |  | 574146.1316 | 546892
Total Households |  | 95691.0219 | 91148.6667
Rest of Iraq
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Anbar | IQ-G01 | 886545.3496 | 490242.116
Babylon | IQ-G06 | 18256.1041 | 10095.266
Baghdad | IQ-G07 | 163558.6023 | 90444.6854
Basrah | IQ-G02 | 2446.4634 | 1352.8461
0
Diyala | IQ-G10 | 196589.4267 | 108710.0807
0
Kerbala | IQ-G12 | 25547.226 | 14127.1127
Kirkuk | IQ-G13 | 301949.0932 | 166971.901
Missan | IQ-G14 | 1992.2148 | 1101.6556
Muthanna | IQ-G03 | 1255.951 | 694.5162
Najaf | IQ-G17 | 25088.5144 | 13873.4543
0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845
0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694
Wassit | IQ-G16 | 8074.2609 | 4464.9072
Total Individuals |  | 2044541.1783 | 1130591
Total Households |  | 340756.8631 | 188431.8333
Mosul / Ninewa
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Ninewa | IQ-G15 | 1264312.6901 | 648858
Total Individuals |  | 1264312.6901 | 648858
Total Households |  | 210718.7817 | 108143

## Jun.17
2017-06-01 |  |  |  | Cluster response Jun.17 |  | First Line |  | Second Line |  | Full Response
Governerate | Admin 1 Code | PEOPLE IN NEED | Target | NFI | Shelter | Emergency NFI | Emergency Shelter | NFI Replenishment | Shelter Upgrade/Repair | NFI3 | Shelter and housing options
Anbar | IQ-G01 | 886545.3496 | 490242.116 | 18126 | 0 | 18126 | 0 | 0 | 0 | 0 | 0
Babylon | IQ-G06 | 18256.1041 | 10095.266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Baghdad | IQ-G07 | 163558.6023 | 90444.6854 | 168 | 1044 | 168 | 702 | 0 | 0 | 0 | 342
Basrah | IQ-G02 | 2446.4634 | 1352.8461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dahuk | IQ-G08 | 275356.378 | 262285.4915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Diyala | IQ-G10 | 196589.4267 | 108710.0807 | 36 | 6 | 36 | 0 | 0 | 6 | 0 | 0
Erbil | IQ-G11 | 233090.3732 | 222025.8108 | 2346 | 2148 | 0 | 0 | 2346 | 1890 | 0 | 258
Kerbala | IQ-G12 | 25547.226 | 14127.1127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kirkuk | IQ-G13 | 301949.0932 | 166971.901 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0
Missan | IQ-G14 | 1992.2148 | 1101.6556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Muthanna | IQ-G03 | 1255.951 | 694.5162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Najaf | IQ-G17 | 25088.5144 | 13873.4543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ninewa | IQ-G15 | 1264312.6901 | 648858 | 62784 | 11964 | 62784 | 3564 | 0 | 5400 | 0 | 3000
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845 | 6414 | 6000 | 6414 | 6000 | 0 | 0 | 0 | 0
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977 | 960 | 4170 | 960 | 30 | 0 | 4140 | 0 | 0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wassit | IQ-G16 | 8074.2609 | 4464.9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Individuals |  | 3883000 | 2326341 | 90864 | 25332 | 88518 | 10296 | 2346 | 11436 | 0 | 3600
Total Households |  | 647166.6667 | 387723.5 | 15144 | 4222 | 14753 | 1716 | 391 | 1906 | 0 | 600
|  |  |  | 3.906% | 1.089%
KR-I
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Dahuk | IQ-G08 | 275356.378 | 262285.4915
Erbil | IQ-G11 | 233090.3732 | 222025.8108
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977
Total Individuals |  | 574146.1316 | 546892
Total Households |  | 95691.0219 | 91148.6667
Rest of Iraq
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Anbar | IQ-G01 | 886545.3496 | 490242.116
Babylon | IQ-G06 | 18256.1041 | 10095.266
Baghdad | IQ-G07 | 163558.6023 | 90444.6854
Basrah | IQ-G02 | 2446.4634 | 1352.8461
0
Diyala | IQ-G10 | 196589.4267 | 108710.0807
0
Kerbala | IQ-G12 | 25547.226 | 14127.1127
Kirkuk | IQ-G13 | 301949.0932 | 166971.901
Missan | IQ-G14 | 1992.2148 | 1101.6556
Muthanna | IQ-G03 | 1255.951 | 694.5162
Najaf | IQ-G17 | 25088.5144 | 13873.4543
0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845
0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694
Wassit | IQ-G16 | 8074.2609 | 4464.9072
Total Individuals |  | 2044541.1783 | 1130591
Total Households |  | 340756.8631 | 188431.8333
Mosul / Ninewa
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Ninewa | IQ-G15 | 1264312.6901 | 648858
Total Individuals |  | 1264312.6901 | 648858
Total Households |  | 210718.7817 | 108143

## Jul.17
2017-07-01 |  |  |  | Cluster response Jul.17 |  | First Line |  | Second Line |  | Full Response
Governerate | Admin 1 Code | PEOPLE IN NEED | Target | NFI | Shelter | Emergency NFI | Emergency Shelter | NFI Replenishment | Shelter Upgrade/Repair | NFI3 | Shelter and housing options
Anbar | IQ-G01 | 886545.3496 | 490242.116 | 2232 | 24 | 2232 | 0 | 0 | 24 | 0 | 0
Babylon | IQ-G06 | 18256.1041 | 10095.266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Baghdad | IQ-G07 | 163558.6023 | 90444.6854 | 180 | 0 | 180 | 0 | 0 | 0 | 0 | 0
Basrah | IQ-G02 | 2446.4634 | 1352.8461 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Dahuk | IQ-G08 | 275356.378 | 262285.4915 | 8136 | 1698 | 8136 | 0 | 0 | 1698 | 0 | 0
Diyala | IQ-G10 | 196589.4267 | 108710.0807 | 0 | 18 | 0 | 0 | 0 | 18 | 0 | 0
Erbil | IQ-G11 | 233090.3732 | 222025.8108 | 83574 | 540 | 83574 | 30 | 0 | 510 | 0 | 0
Kerbala | IQ-G12 | 25547.226 | 14127.1127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kirkuk | IQ-G13 | 301949.0932 | 166971.901 | 11286 | 2034 | 11286 | 534 | 0 | 1500 | 0 | 0
Missan | IQ-G14 | 1992.2148 | 1101.6556 | 36 | 0 | 36 | 0 | 0 | 0 | 0 | 0
Muthanna | IQ-G03 | 1255.951 | 694.5162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Najaf | IQ-G17 | 25088.5144 | 13873.4543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ninewa | IQ-G15 | 1264312.6901 | 648858 | 255408 | 46224 | 254088 | 11226 | 1320 | 34998 | 0 | 0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845 | 4794 | 4794 | 4794 | 4794 | 0 | 0 | 0 | 0
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977 | 660 | 60 | 660 | 36 | 0 | 24 | 0 | 0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wassit | IQ-G16 | 8074.2609 | 4464.9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Individuals |  | 3883000 | 2326341 | 366306 | 55392 | 364986 | 16620 | 1320 | 38772 | 0 | 0
Total Households |  | 647166.6667 | 387723.5 | 61051 | 9232 | 60831 | 2770 | 220 | 6462 | 0 | 0
|  |  |  | 15.75% | 2.381%
KR-I
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Dahuk | IQ-G08 | 275356.378 | 262285.4915
Erbil | IQ-G11 | 233090.3732 | 222025.8108
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977
Total Individuals |  | 574146.1316 | 546892
Total Households |  | 95691.0219 | 91148.6667
Rest of Iraq
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Anbar | IQ-G01 | 886545.3496 | 490242.116
Babylon | IQ-G06 | 18256.1041 | 10095.266
Baghdad | IQ-G07 | 163558.6023 | 90444.6854
Basrah | IQ-G02 | 2446.4634 | 1352.8461
0
Diyala | IQ-G10 | 196589.4267 | 108710.0807
0
Kerbala | IQ-G12 | 25547.226 | 14127.1127
Kirkuk | IQ-G13 | 301949.0932 | 166971.901
Missan | IQ-G14 | 1992.2148 | 1101.6556
Muthanna | IQ-G03 | 1255.951 | 694.5162
Najaf | IQ-G17 | 25088.5144 | 13873.4543
0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845
0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694
Wassit | IQ-G16 | 8074.2609 | 4464.9072
Total Individuals |  | 2044541.1783 | 1130591
Total Households |  | 340756.8631 | 188431.8333
Mosul / Ninewa
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Ninewa | IQ-G15 | 1264312.6901 | 648858
Total Individuals |  | 1264312.6901 | 648858
Total Households |  | 210718.7817 | 108143

## Aug.17
2017-08-01 |  |  |  | Cluster response Aug.17 |  | First Line |  | Second Line |  | Full Response
Governerate | Admin 1 Code | PEOPLE IN NEED | Target | NFI | Shelter | Emergency NFI | Emergency Shelter | NFI Replenishment | Shelter Upgrade/Repair | NFI3 | Shelter and housing options
Anbar | IQ-G01 | 886545.3496 | 490242.116 | 26964 | 14100 | 26964 | 6972 | 0 | 7128 | 0 | 0
Babylon | IQ-G06 | 18256.1041 | 10095.266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Baghdad | IQ-G07 | 163558.6023 | 90444.6854 | 6 | 1506 | 6 | 6 | 0 | 1500 | 0 | 0
Basrah | IQ-G02 | 2446.4634 | 1352.8461 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Dahuk | IQ-G08 | 275356.378 | 262285.4915 | 0 | 546 | 0 | 0 | 0 | 546 | 0 | 0
Diyala | IQ-G10 | 196589.4267 | 108710.0807 | 0 | 228 | 0 | 0 | 0 | 228 | 0 | 0
Erbil | IQ-G11 | 233090.3732 | 222025.8108 | 900 | 3114 | 900 | 180 | 0 | 2934 | 0 | 0
Kerbala | IQ-G12 | 25547.226 | 14127.1127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kirkuk | IQ-G13 | 301949.0932 | 166971.901 | 20508 | 9462 | 18762 | 654 | 1746 | 8808 | 0 | 0
Missan | IQ-G14 | 1992.2148 | 1101.6556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Muthanna | IQ-G03 | 1255.951 | 694.5162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Najaf | IQ-G17 | 25088.5144 | 13873.4543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ninewa | IQ-G15 | 1264312.6901 | 648858 | 35334 | 63396 | 35334 | 59340 | 0 | 4056 | 0 | 0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845 | 8370 | 3000 | 8370 | 0 | 0 | 3000 | 0 | 0
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977 | 6 | 6438 | 6 | 48 | 0 | 6390 | 0 | 0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wassit | IQ-G16 | 8074.2609 | 4464.9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Individuals |  | 3883000 | 2326341 | 92088 | 101790 | 90342 | 67200 | 1746 | 34590 | 0 | 0
Total Households |  | 647166.6667 | 387723.5 | 15348 | 16965 | 15057 | 11200 | 291 | 5765 | 0 | 0
|  |  |  | 3.958% | 4.376%
KR-I
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Dahuk | IQ-G08 | 275356.378 | 262285.4915
Erbil | IQ-G11 | 233090.3732 | 222025.8108
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977
Total Individuals |  | 574146.1316 | 546892
Total Households |  | 95691.0219 | 91148.6667
Rest of Iraq
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Anbar | IQ-G01 | 886545.3496 | 490242.116
Babylon | IQ-G06 | 18256.1041 | 10095.266
Baghdad | IQ-G07 | 163558.6023 | 90444.6854
Basrah | IQ-G02 | 2446.4634 | 1352.8461
0
Diyala | IQ-G10 | 196589.4267 | 108710.0807
0
Kerbala | IQ-G12 | 25547.226 | 14127.1127
Kirkuk | IQ-G13 | 301949.0932 | 166971.901
Missan | IQ-G14 | 1992.2148 | 1101.6556
Muthanna | IQ-G03 | 1255.951 | 694.5162
Najaf | IQ-G17 | 25088.5144 | 13873.4543
0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845
0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694
Wassit | IQ-G16 | 8074.2609 | 4464.9072
Total Individuals |  | 2044541.1783 | 1130591
Total Households |  | 340756.8631 | 188431.8333
Mosul / Ninewa
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Ninewa | IQ-G15 | 1264312.6901 | 648858
Total Individuals |  | 1264312.6901 | 648858
Total Households |  | 210718.7817 | 108143

## Sept.17
2017-09-01 |  |  |  | Cluster response Sept.17 |  | First Line |  | Second Line |  | Full Response
Governerate | Admin 1 Code | PEOPLE IN NEED | Target | NFI | Shelter | Emergency NFI | Emergency Shelter | NFI Replenishment | Shelter Upgrade/Repair | NFI3 | Shelter and housing options
Anbar | IQ-G01 | 886545.3496 | 490242.116 | 14736 | 3048 | 14736 | 3042 | 0 | 6 | 0 | 0
Babylon | IQ-G06 | 18256.1041 | 10095.266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Baghdad | IQ-G07 | 163558.6023 | 90444.6854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Basrah | IQ-G02 | 2446.4634 | 1352.8461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dahuk | IQ-G08 | 275356.378 | 262285.4915 | 66 | 54312 | 66 | 36 | 0 | 54276 | 0 | 0
Diyala | IQ-G10 | 196589.4267 | 108710.0807 | 1230 | 18 | 1230 | 12 | 0 | 6 | 0 | 0
Erbil | IQ-G11 | 233090.3732 | 222025.8108 | 0 | 5238 | 0 | 4242 | 0 | 996 | 0 | 0
Kerbala | IQ-G12 | 25547.226 | 14127.1127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kirkuk | IQ-G13 | 301949.0932 | 166971.901 | 0 | 1164 | 0 | 300 | 0 | 864 | 0 | 0
Missan | IQ-G14 | 1992.2148 | 1101.6556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Muthanna | IQ-G03 | 1255.951 | 694.5162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Najaf | IQ-G17 | 25088.5144 | 13873.4543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ninewa | IQ-G15 | 1264312.6901 | 648858 | 9930 | 167892 | 9930 | 110256 | 0 | 57636 | 0 | 0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845 | 2628 | 5100 | 2628 | 5100 | 0 | 0 | 0 | 0
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977 | 10152 | 54 | 10152 | 48 | 0 | 6 | 0 | 0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wassit | IQ-G16 | 8074.2609 | 4464.9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Individuals |  | 3883000 | 2326341 | 38742 | 236826 | 38742 | 123036 | 0 | 113790 | 0 | 0
Total Households |  | 647166.6667 | 387723.5 | 6457 | 39471 | 6457 | 20506 | 0 | 18965 | 0 | 0
|  |  |  | 1.665% | 10.18%
KR-I
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Dahuk | IQ-G08 | 275356.378 | 262285.4915
Erbil | IQ-G11 | 233090.3732 | 222025.8108
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977
Total Individuals |  | 574146.1316 | 546892
Total Households |  | 95691.0219 | 91148.6667
Rest of Iraq
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Anbar | IQ-G01 | 886545.3496 | 490242.116
Babylon | IQ-G06 | 18256.1041 | 10095.266
Baghdad | IQ-G07 | 163558.6023 | 90444.6854
Basrah | IQ-G02 | 2446.4634 | 1352.8461
0
Diyala | IQ-G10 | 196589.4267 | 108710.0807
0
Kerbala | IQ-G12 | 25547.226 | 14127.1127
Kirkuk | IQ-G13 | 301949.0932 | 166971.901
Missan | IQ-G14 | 1992.2148 | 1101.6556
Muthanna | IQ-G03 | 1255.951 | 694.5162
Najaf | IQ-G17 | 25088.5144 | 13873.4543
0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845
0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694
Wassit | IQ-G16 | 8074.2609 | 4464.9072
Total Individuals |  | 2044541.1783 | 1130591
Total Households |  | 340756.8631 | 188431.8333
Mosul / Ninewa
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Ninewa | IQ-G15 | 1264312.6901 | 648858
Total Individuals |  | 1264312.6901 | 648858
Total Households |  | 210718.7817 | 108143

## Consolidated 2017_Response
Summary Since Jan.17 |  |  |  | Cluster response since Jan.17 |  | First Line |  | Second Line |  | Full Response
Governerate | Admin 1 Code | PEOPLE IN NEED | Target | NFI | Shelter | Emergency NFI | Emergency Shelter | NFI Replenishment | Shelter Upgrade/Repair | NFI3 | Shelter and housing options
Anbar | IQ-G01 | 886545.3496 | 490242.116 | 93396 | 25032 | 93396 | 13194 | 0 | 11682 | 0 | 156
Babylon | IQ-G06 | 18256.1041 | 10095.266 | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 210
Baghdad | IQ-G07 | 163558.6023 | 90444.6854 | 5292 | 5964 | 5292 | 708 | 0 | 3288 | 0 | 1968
Basrah | IQ-G02 | 2446.4634 | 1352.8461 | 720 | 0 | 720 | 0 | 0 | 0 | 0 | 0
Dahuk | IQ-G08 | 275356.378 | 262285.4915 | 8226 | 64056 | 8226 | 36 | 0 | 64020 | 0 | 0
Diyala | IQ-G10 | 196589.4267 | 108710.0807 | 6924 | 3666 | 6924 | 12 | 0 | 3354 | 0 | 300
Erbil | IQ-G11 | 233090.3732 | 222025.8108 | 139050 | 11880 | 124824 | 4452 | 14226 | 6330 | 0 | 1098
Kerbala | IQ-G12 | 25547.226 | 14127.1127 | 0 | 204 | 0 | 0 | 0 | 0 | 0 | 204
Kirkuk | IQ-G13 | 301949.0932 | 166971.901 | 76980 | 115614 | 75234 | 65928 | 1746 | 49572 | 0 | 114
Missan | IQ-G14 | 1992.2148 | 1101.6556 | 36 | 0 | 36 | 0 | 0 | 0 | 0 | 0
Muthanna | IQ-G03 | 1255.951 | 694.5162 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0
Najaf | IQ-G17 | 25088.5144 | 13873.4543 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 240
Ninewa | IQ-G15 | 1264312.6901 | 648858 | 1178496 | 581154 | 1177176 | 443562 | 1320 | 134592 | 0 | 3000
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049 | 300 | 0 | 300 | 0 | 0 | 0 | 0 | 0
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845 | 118692 | 94236 | 118692 | 60342 | 0 | 32130 | 0 | 1764
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977 | 11940 | 12972 | 11940 | 168 | 0 | 12804 | 0 | 0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694 | 318 | 0 | 318 | 0 | 0 | 0 | 0 | 0
Wassit | IQ-G16 | 8074.2609 | 4464.9072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Individuals |  | 3883000 | 2326341 | 1640382 | 915228 | 1623090 | 588402 | 17292 | 317772 | 0 | 9054
Total Households |  | 647166.6667 | 387723.5 | 273397 | 152538 | 270515 | 98067 | 2882 | 52962 | 0 | 1509
|  |  |  | 70.51% | 39.34%
KR-I
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Dahuk | IQ-G08 | 275356.378 | 262285.4915
Erbil | IQ-G11 | 233090.3732 | 222025.8108
Sulaymaniyah | IQ-G05 | 65699.3803 | 62580.6977
Total Individuals |  | 574146.1316 | 546892
Total Households |  | 95691.0219 | 91148.6667
Rest of Iraq
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Anbar | IQ-G01 | 886545.3496 | 490242.116
Babylon | IQ-G06 | 18256.1041 | 10095.266
Baghdad | IQ-G07 | 163558.6023 | 90444.6854
Basrah | IQ-G02 | 2446.4634 | 1352.8461
0
Diyala | IQ-G10 | 196589.4267 | 108710.0807
0
Kerbala | IQ-G12 | 25547.226 | 14127.1127
Kirkuk | IQ-G13 | 301949.0932 | 166971.901
Missan | IQ-G14 | 1992.2148 | 1101.6556
Muthanna | IQ-G03 | 1255.951 | 694.5162
Najaf | IQ-G17 | 25088.5144 | 13873.4543
0
Qadissiya | IQ-G04 | 6864.6296 | 3796.0049
Salah al-Din | IQ-G18 | 404341.4989 | 223592.8845
0
Thi-Qar | IQ-G09 | 2031.8434 | 1123.5694
Wassit | IQ-G16 | 8074.2609 | 4464.9072
Total Individuals |  | 2044541.1783 | 1130591
Total Households |  | 340756.8631 | 188431.8333
Mosul / Ninewa
Governerate | Admin 1 Code | PEOPLE IN NEED | Target
Ninewa | IQ-G15 | 1264312.6901 | 648858
Total Individuals |  | 1264312.6901 | 648858
Total Households |  | 210718.7817 | 108143

## PMR May.17
Monitoring Matrix ¦ Objectives Indicators | [8 empty] | Update | 2017-05-31
These are Cluster overall achievements per objectives and indicators. However major gaps to be considered remain at governorate level.
Cluster Objective 1: | Provide safe, appropriate emergency shelter and distribute critical life-saving non-food items to vulnerable populations in priority locations
Supporting Strategic Objectives: | SO1, SO2 | [6 empty] | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target
HH/people
No of people supported through the provision of emergency shelter | Provision of tents and emergency shelter kits | IDPs, Returnees | All governorates | 56,603/339,618 | 344258 | 45% | 55% | 61875 | 371250 | 107.8%
No of people supported through of the distribution NFI kits | Distributing non-food item kits (Mobile or Basic, Seasonal Top-up or clothing) | IDPs, Returnees, Stayees, Hosts | All governorates | 212,818/1,276,909 | 1190204 | 45% | 55% | 173417 | 1040502 | 87.42%
Cluster Objective 2: | Upgrade and repair basic shelters and replenish core household items for vulnerable populations.
Supporting Strategic Objectives: | SO1, SO2, SO3 | [6 empty] | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target
HH/people
No of people supported with tent replacements | Replacing degraded and damaged tents | IDPs | All governorates | 6,944/41,664 | 256530 | 45% | 55% | 28 | 168 | 0.06549%
No of people supported with shelter upgrade with concrete slabs. | Upgrading shelter plots (in existing camp) | IDPs | All governorates | 11,925/71,550 | 12234 | 45% | 55% | 1030 | 6180 | 50.51%
No of people supported with basic shelter upgrades or repair | Upgrade and repair basic shelters for vulnerable populations | IDPs, Returnees, Stayees, Hosts | All governorates | 23,899/143,394 | 382978 | 45% | 55% | 18806 | 112836 | 29.46%
No of people supported with replenishment of core household items | Replenish core household items for vulnerable populations | IDPs, Returnees, Stayees, Hosts | All governorates | 8,976/53,856 | 100246 | 45% | 55% | 1980 | 11880 | 11.85%
Cluster Objective 3: | Expand safe, dignified shelter and housing options for vulnerable households in accordance with agreed standards.
Supporting Strategic Objectives: | SO2, SO3 | [6 empty] | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target
HH/people
No of people supported with safe, dignified shelter and housing options through repair of heavily damaged houses | Upgrade or Repair Unfinished and Abandoned / War Damaged buildings | IDPs, Returnees, Stayees, Hosts | All governorates | 6,608/39,648 | 41534 | 45% | 55% | 909 | 5454 | 13.13%

## PMR Jun.17
Monitoring Matrix ¦ Objectives Indicators | [8 empty] | Update | 2017-06-30
These are Cluster overall achievements per objectives and indicators. However major gaps to be considered remain at governorate level.
Cluster Objective 1: | Provide safe, appropriate emergency shelter and distribute critical life-saving non-food items to vulnerable populations in priority locations
Supporting Strategic Objectives: | SO1, SO2 | [6 empty] | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target
HH/people
No of people supported through the provision of emergency shelter | Provision of tents and emergency shelter kits | IDPs, Returnees | All governorates | 56,603/339,618 | 344258 | 45% | 55% | 63591 | 381546 | 110.8%
No of people supported through of the distribution NFI kits | Distributing non-food item kits (Mobile or Basic, Seasonal Top-up or clothing) | IDPs, Returnees, Stayees, Hosts | All governorates | 212,818/1,276,909 | 1190204 | 45% | 55% | 188170 | 1129020 | 94.86%
Cluster Objective 2: | Upgrade and repair basic shelters and replenish core household items for vulnerable populations.
Supporting Strategic Objectives: | SO1, SO2, SO3 | [6 empty] | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target
HH/people
No of people supported with tent replacements | Replacing degraded and damaged tents | IDPs | All governorates | 6,944/41,664 | 256530 | 45% | 55% | 29 | 174 | 0.06783%
No of people supported with shelter upgrade with concrete slabs. | Upgrading shelter plots (in existing camp) | IDPs | All governorates | 11,925/71,550 | 12234 | 45% | 55% | 1030 | 6180 | 50.51%
No of people supported with basic shelter upgrades or repair | Upgrade and repair basic shelters for vulnerable populations | IDPs, Returnees, Stayees, Hosts | All governorates | 23,899/143,394 | 382978 | 45% | 55% | 20711 | 124266 | 32.45%
No of people supported with replenishment of core household items | Replenish core household items for vulnerable populations | IDPs, Returnees, Stayees, Hosts | All governorates | 8,976/53,856 | 100246 | 45% | 55% | 2371 | 14226 | 14.19%
Cluster Objective 3: | Expand safe, dignified shelter and housing options for vulnerable households in accordance with agreed standards.
Supporting Strategic Objectives: | SO2, SO3 | [6 empty] | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target
HH/people
No of people supported with safe, dignified shelter and housing options through repair of heavily damaged houses | Upgrade or Repair Unfinished and Abandoned / War Damaged buildings | IDPs, Returnees, Stayees, Hosts | All governorates | 6,608/39,648 | 41534 | 45% | 55% | 1509 | 9054 | 21.8%

## PMR Jul.17
Monitoring Matrix ¦ Objectives Indicators | [8 empty] | Update | 2017-07-30
These are Cluster overall achievements per objectives and indicators. However major gaps to be considered remain at governorate level.
Cluster Objective 1: | Provide safe, appropriate emergency shelter and distribute critical life-saving non-food items to vulnerable populations in priority locations
Supporting Strategic Objectives: | SO1, SO2 | [6 empty] | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target
HH/people
No of people supported through the provision of emergency shelter | Provision of tents and emergency shelter kits | IDPs, Returnees | All governorates | 56,603/339,618 | 344258 | 45% | 55% | 66361 | 398166 | 115.7%
No of people supported through of the distribution NFI kits | Distributing non-food item kits (Mobile or Basic, Seasonal Top-up or clothing) | IDPs, Returnees, Stayees, Hosts | All governorates | 212,818/1,276,909 | 1190204 | 45% | 55% | 249001 | 1494006 | 125.5%
Cluster Objective 2: | Upgrade and repair basic shelters and replenish core household items for vulnerable populations.
Supporting Strategic Objectives: | SO1, SO2, SO3 | [6 empty] | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target
HH/people
No of people supported with tent replacements | Replacing degraded and damaged tents | IDPs | All governorates | 6,944/41,664 | 256530 | 45% | 55% | 38 | 228 | 0.08888%
No of people supported with shelter upgrade with concrete slabs. | Upgrading shelter plots (in existing camp) | IDPs | All governorates | 11,925/71,550 | 12234 | 45% | 55% | 5334 | 32004 | 261.6%
No of people supported with basic shelter upgrades or repair | Upgrade and repair basic shelters for vulnerable populations | IDPs, Returnees, Stayees, Hosts | All governorates | 23,899/143,394 | 382978 | 45% | 55% | 22860 | 137160 | 35.81%
No of people supported with replenishment of core household items | Replenish core household items for vulnerable populations | IDPs, Returnees, Stayees, Hosts | All governorates | 8,976/53,856 | 100246 | 45% | 55% | 2591 | 15546 | 15.51%
Cluster Objective 3: | Expand safe, dignified shelter and housing options for vulnerable households in accordance with agreed standards.
Supporting Strategic Objectives: | SO2, SO3 | [6 empty] | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target
HH/people
No of people supported with safe, dignified shelter and housing options through repair of heavily damaged houses | Upgrade or Repair Unfinished and Abandoned / War Damaged buildings | IDPs, Returnees, Stayees, Hosts | All governorates | 6,608/39,648 | 41534 | 45% | 55% | 1509 | 9054 | 21.8%

## PMR Aug.17
Monitoring Matrix ¦ Objectives Indicators | [8 empty] | Update | 2017-08-31
These are Cluster overall achievements per objectives and indicators. However major gaps to be considered remain at governorate level.
Cluster Objective 1: | Provide safe, appropriate emergency shelter and distribute critical life-saving non-food items to vulnerable populations in priority locations
Supporting Strategic Objectives: | SO1, SO2 | [6 empty] | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target
HH/people
No of people supported through the provision of emergency shelter | Provision of tents and emergency shelter kits | IDPs, Returnees | All governorates | 56,603/339,618 | 344258 | 45% | 55% | 77561 | 465366 | 135.2%
No of people supported through of the distribution NFI kits | Distributing non-food item kits (Mobile or Basic, Seasonal Top-up or clothing) | IDPs, Returnees, Stayees, Hosts | All governorates | 212,818/1,276,909 | 1190204 | 45% | 55% | 264058 | 1584348 | 133.1%
Cluster Objective 2: | Upgrade and repair basic shelters and replenish core household items for vulnerable populations.
Supporting Strategic Objectives: | SO1, SO2, SO3 | [6 empty] | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target
HH/people
No of people supported with tent replacements | Replacing degraded and damaged tents | IDPs | All governorates | 6,944/41,664 | 256530 | 45% | 55% | 356 | 2136 | 0.8327%
No of people supported with shelter upgrade with concrete slabs. | Upgrading shelter plots (in existing camp) | IDPs | All governorates | 11,925/71,550 | 12234 | 45% | 55% | 5349 | 32094 | 262.3%
No of people supported with basic shelter upgrades or repair | Upgrade and repair basic shelters for vulnerable populations | IDPs, Returnees, Stayees, Hosts | All governorates | 23,899/143,394 | 382978 | 45% | 55% | 28292 | 169752 | 44.32%
No of people supported with replenishment of core household items | Replenish core household items for vulnerable populations | IDPs, Returnees, Stayees, Hosts | All governorates | 8,976/53,856 | 100246 | 45% | 55% | 2882 | 17292 | 17.25%
Cluster Objective 3: | Expand safe, dignified shelter and housing options for vulnerable households in accordance with agreed standards.
Supporting Strategic Objectives: | SO2, SO3 | [6 empty] | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target
HH/people
No of people supported with safe, dignified shelter and housing options through repair of heavily damaged houses | Upgrade or Repair Unfinished and Abandoned / War Damaged buildings | IDPs, Returnees, Stayees, Hosts | All governorates | 6,608/39,648 | 41534 | 45% | 55% | 1509 | 9054 | 21.8%

## PMR Sept.17
Monitoring Matrix ¦ Objectives Indicators | [8 empty] | Update | 2017-09-30
These are Cluster overall achievements per objectives and indicators. However major gaps to be considered remain at governorate level.
Cluster Objective 1: | Provide safe, appropriate emergency shelter and distribute critical life-saving non-food items to vulnerable populations in priority locations
Supporting Strategic Objectives: | SO1, SO2 | [6 empty] | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target
HH/people
No of people supported through the provision of emergency shelter | Provision of tents and emergency shelter kits | IDPs, Returnees | All governorates | 56,603/339,618 | 344258 | 45% | 55% | 98067 | 588402 | 170.9%
No of people supported through of the distribution NFI kits | Distributing non-food item kits (Mobile or Basic, Seasonal Top-up or clothing) | IDPs, Returnees, Stayees, Hosts | All governorates | 212,818/1,276,909 | 1190204 | 45% | 55% | 270515 | 1623090 | 136.4%
Cluster Objective 2: | Upgrade and repair basic shelters and replenish core household items for vulnerable populations.
Supporting Strategic Objectives: | SO1, SO2, SO3 | [6 empty] | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target
HH/people
No of people supported with tent replacements | Replacing degraded and damaged tents | IDPs | All governorates | 6,944/41,664 | 256530 | 45% | 55% | 18869 | 113214 | 44.13% | Significant increase due to
MoDM interventions in Esian, Bardarash, Chamishku, Kabarto 1&2 and Mamilian Camps
No of people supported with shelter upgrade with concrete slabs. | Upgrading shelter plots (in existing camp) | IDPs | All governorates | 11,925/71,550 | 12234 | 45% | 55% | 5349 | 32094 | 262.3%
No of people supported with basic shelter upgrades or repair | Upgrade and repair basic shelters for vulnerable populations | IDPs, Returnees, Stayees, Hosts | All governorates | 23,899/143,394 | 382978 | 45% | 55% | 28744 | 172464 | 45.03%
No of people supported with replenishment of core household items | Replenish core household items for vulnerable populations | IDPs, Returnees, Stayees, Hosts | All governorates | 8,976/53,856 | 100246 | 45% | 55% | 2882 | 17292 | 17.25%
Cluster Objective 3: | Expand safe, dignified shelter and housing options for vulnerable households in accordance with agreed standards.
Supporting Strategic Objectives: | SO2, SO3 | [6 empty] | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target
HH/people
No of people supported with safe, dignified shelter and housing options through repair of heavily damaged houses | Upgrade or Repair (Unfinished and Abandoned / War Damaged) buildings | IDPs, Returnees, Stayees, Hosts | All governorates | 6,608/39,648 | 41534 | 45% | 55% | 1509 | 9054 | 21.8%

## Consolidated 2017_PMR
CONSOLIDATED - 2017 PMR
Monitoring Matrix ¦ Objectives Indicators
These are Cluster overall achievements per objectives and indicators. However major gaps to be considered remain at governorate level.
Cluster Objective 1: | Provide safe, appropriate emergency shelter and distribute critical life-saving non-food items to vulnerable populations in priority locations | [6 empty] | 2017-05-31 |  |  | 2017-06-30 |  |  | 2017-07-30 |  |  | 2017-08-31 |  |  | 2017-09-30
Supporting Strategic Objectives: | SO1, SO2 | [6 empty] | Reached |  |  | Reached |  |  | Reached |  |  | Reached |  |  | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target | HH | Ind. | Coverage against target | HH | Ind. | Coverage against target | HH | Ind. | Coverage against target | HH | Ind. | Coverage against target
HH/people
No of people supported through the provision of emergency shelter | Provision of tents and emergency shelter kits | IDPs, Returnees | All governorates | 56,603/339,618 | 344258 | 45% | 55% | 61875 | 371250 | 107.8% | 63591 | 381546 | 110.8% | 66361 | 398166 | 115.7% | 77561 | 465366 | 135.2% | 98067 | 588402 | 170.9%
No of people supported through of the distribution NFI kits | Distributing non-food item kits (Mobile or Basic, Seasonal Top-up or clothing) | IDPs, Returnees, Stayees, Hosts | All governorates | 212,818/1,276,909 | 1190204 | 45% | 55% | 173417 | 1040502 | 87.42% | 188170 | 1129020 | 94.86% | 249001 | 1494006 | 125.5% | 264058 | 1584348 | 133.1% | 270515 | 1623090 | 136.4%
Cluster Objective 2: | Upgrade and repair basic shelters and replenish core household items for vulnerable populations. | [6 empty] | 2017-05-31 |  |  | 2017-06-30 |  |  | 2017-07-30 |  |  | 2017-08-31 |  |  | 2017-09-30
Supporting Strategic Objectives: | SO1, SO2, SO3 | [6 empty] | Reached |  |  | Reached |  |  | Reached |  |  | Reached |  |  | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target | HH | Ind. | Coverage against target | HH | Ind. | Coverage against target | HH | Ind. | Coverage against target | HH | Ind. | Coverage against target
HH/people
No of people supported with tent replacements | Replacing degraded and damaged tents | IDPs | All governorates | 6,944/41,664 | 256530 | 45% | 55% | 28 | 168 | 0.06549% | 29 | 174 | 0.06783% | 38 | 228 | 0.08888% | 356 | 2136 | 0.8327% | 18869 | 113214 | 44.13%
No of people supported with shelter upgrade with concrete slabs. | Upgrading shelter plots (in existing camp) | IDPs | All governorates | 11,925/71,550 | 12234 | 45% | 55% | 1030 | 6180 | 50.51% | 1030 | 6180 | 50.51% | 5334 | 32004 | 261.6% | 5349 | 32094 | 262.3% | 5349 | 32094 | 262.3%
No of people supported with basic shelter upgrades or repair | Upgrade and repair basic shelters for vulnerable populations | IDPs, Returnees, Stayees, Hosts | All governorates | 23,899/143,394 | 382978 | 45% | 55% | 18806 | 112836 | 29.46% | 20711 | 124266 | 32.45% | 22860 | 137160 | 35.81% | 28292 | 169752 | 44.32% | 28744 | 172464 | 45.03%
No of people supported with replenishment of core household items | Replenish core household items for vulnerable populations | IDPs, Returnees, Stayees, Hosts | All governorates | 8,976/53,856 | 100246 | 45% | 55% | 1980 | 11880 | 11.85% | 2371 | 14226 | 14.19% | 2591 | 15546 | 15.51% | 2882 | 17292 | 17.25% | 2882 | 17292 | 17.25%
Cluster Objective 3: | Expand safe, dignified shelter and housing options for vulnerable households in accordance with agreed standards. | [6 empty] | 2017-05-31 |  |  | 2017-06-30 |  |  | 2017-07-30 |  |  | 2017-08-31 |  |  | 2017-09-30
Supporting Strategic Objectives: | SO2, SO3 | [6 empty] | Reached |  |  | Reached |  |  | Reached |  |  | Reached |  |  | Reached
Indicator: | Activities | In Need | Governorate | Baseline | Target | Male | Female | HH | Ind. | Coverage against target | HH | Ind. | Coverage against target | HH | Ind. | Coverage against target | HH | Ind. | Coverage against target | HH | Ind. | Coverage against target
HH/people
No of people supported with safe, dignified shelter and housing options through repair of heavily damaged houses | Upgrade or Repair Unfinished and Abandoned / War Damaged buildings | IDPs, Returnees, Stayees, Hosts | All governorates | 6,608/39,648 | 41534 | 45% | 55% | 909 | 5454 | 13.13% | 1509 | 9054 | 21.8% | 1509 | 9054 | 21.8% | 1509 | 9054 | 21.8% | 1509 | 9054 | 21.8%