Sorlands floods – Draft Shelter Cluster strategy (For Review)

September 2016

Status

| Strategy Status | Version | Status | Effective date | Next revision |
| --- | --- | --- | --- | --- |
|  | Preliminary | To be endorsed by cluster members/draft | 28/09/2016 |  |

Shelter Cluster Structure

| Response name | Sorlands Floods response |
| --- | --- |
| Cluster Lead Agency | IFRC – Cluster activated by RC Sorland on 25/09/16 |
| Cluster Coordinator Contact | Name: Michael Gloeckle E-Mail: coord.sorland@sheltercluster.org Phone: +47 96864924 ¦ Skype: michaelgloeckle |
| Government counterpart agency and contact | Agency: LEMA Name: Email: Lema.secretariat@gmail.com Mobile: 922 65264 |
| Co-leads | TBC – UNHCR currently supporting with technical and IM support |
| Strategic Advisory Group (SAG) - Agencies | IFRC/UNHCR/IOM/Medair/Handicap International TOR for SAG developed |
| Endorsing Cluster partner Members |  |
| Structure of the Cluster | The Shelter Cluster consists of the following components: A dedicated Coordination Team that manages the core functions of the cluster, usually coordination, information management and technical support. Main Cluster Meetings which are open to all shelter actors. The Strategic Advisory Group (SAG), a smaller group of organizations that represents the cluster and provides strategic direction. Technical Working Groups (TWiGs) that work on specific issues such as shelter design, technical specifications, land issues, housing, land and property rights, reconstruction planning, |

Shelter Cluster Strategy

| Situation | Tropical storm Windblown is likely to affect up to 2 million people across southern Sorland, half of whom are living in the most affected municipalities of Farsund and Lyngdale. The Category Three storm made landfall on September 25, damaging critical infrastructure, including communications, roads, bridges and power lines. The storm follows severe flooding, which had already affected 150,000 people in the same area. Rains are expected to continue until November and further flooding is possible, Forty percent of houses have been destroyed in the worst affected areas, up to 80 percent in some villages. The local health system is overwhelmed, and health facilities have been closed or damaged by the storm. Malaria and water borne diseases have spiked and there is a risk of cholera, especially in the overcrowded evacuation centers. |
| --- | --- |

| Country Strategic Response Plan (SRP) Objectives | <example> List here the country level strategic priorities that the shelter cluster is working towards addressing. The SRP will have a 3-5 strategic objectives for the country defined by the HCT. |
| --- | --- |
| Cluster Objectives | Objective 1 - Provide life-saving, appropriate & safe sheltering and settlement solutions to targeted populations in need while discouraging further displacement where possible and appropriate. Objective 2 - Supporting the return of displaced populations to their original location where safe and appropriate. Objective 3 - Facilitate self-recovery through provision of durable solutions, repairs, retrofitting, and reconstruction, and promotion of Building Back Safer (BBS) Objective 4 - Assist communities to self-Identify hazards and risks and design mitigation measures – mitigation and contingency planning |
| Key Issues | Thousands of households do not have a proper place to live. Some because they cannot rebuild/repair their houses and some others because the flooding of the river has caused them to leave their villages. The government is requesting support to the international community for those thousands of households without shelter and in repairing destroyed and damaged houses. People out in the open need support immediately. Based on DTM figures and UNDAC assessment results from Vest-Agder and Telemarken, the cluster estimates that 39,504 households (197,520 people) have been displaced across various locations (70,070 people in host communities and 127,450 people in camps). National government figures estimate that a total of 454,000 people are displaced (204,000 people in host communities and 186,000 people in camps). Shelter needs range from leaking roofs, lack of partitioning, lack of heating, overcrowding to difficult access for the elderly and people with special needs. In Rogaland, 45% of the houses are slightly damaged and 45% severely damaged, in Vest-Agder this is 40% and 30% respectively. UNOSAT risk mapping shows that Siggersvall and Lista Stadium are in high risk flood zones, the people staying in these sites will need to be relocated. It is not clear yet when the floods will subside, but damage assessments are needed in the areas most affected by the hurricane (high wind speed zones). |
| Assessments | List assessments carried out or to be carried out with time frame and mention reports: DTM displaced tracking matrix survey UNDAC rapid needs assessment Humanitarian needs overview Detailed shelter assessments of settlements, hosting communities and return locations. |
| Monitoring and Evaluation | Agencies report to cluster on xxxx, cluster will collate data on XXX, and be responsible XXX, Evalutions to be carried out on coordination and response |

Response Plan

| Target Groups | Estimated Total Caseload #HH | Emergency Activities (up to 8 weeks ) | Recovery Activities (up to 9 months – if applicable) | Targets/ Assumptions/Notes |
| --- | --- | --- | --- | --- |
|  |  | Target #HH | Approved Interventions and Standards | Target #HH | Approved Interventions and Standards |  |
| Displaced | HH located in collective centres | 9,240 | 20 No. | Collective centre up-grades | 9,240 | Technical training, for return |  |
|  |  |  | 9,240 | Basic house hold kits | 5,000 | Conditional cash-support for shelter | House hold surveys and assessments to ensure no duplication with non-dispersed in severely damaged households |
|  | Informally self-settled households (dispersed, unplanned camps, renting) | 13,250 | 13,250 | Emergency shelter kits | 13,250 | Technical training, for return |  |
|  |  |  | 6,000 | Tents (UNHCR family type) | 13,250 | Conditional cash-support for shelter | House hold surveys and assessments to ensure no duplication with non-dispersed in severely damaged households |
|  |  |  | 7,250 | Rental support | Item | HLP support to facilitate returns |  |
|  |  |  | 10 | Child friendly places |  |  |  |
|  |  |  | 6,000 | Winterization of shelters |  |  |  |
|  | HH that are located in planned camps | 3,000 | 500 | Emergency shelters | 3,000 | Technical training, for return |  |
|  |  |  | Item | Site upgrades (roads, drains, lighting, etc...) | 3,000 | Conditional cash-support for shelter |  |
|  |  |  | Item | Site facilities (health, community, services, etc...) | Item | HLP support to facilitate returns |  |
|  |  |  | 500 | Winterization of shelters | Item | Camp de-commissioning |  |
|  |  |  | 10 | Child friendly spaces |  |  |  |
|  | SUBTOTAL | 25,490 |  |  |  |  |  |
| Non Displaced | IDPs in Host families requiring assistance | 14,014 | 7,000 | Emergency shelter | 14,014 | Conditional cash-support for shelter |  |
|  |  |  | 14,014 | Basic house hold kits |  |  |  |
|  | HH with severely damaged housing | 60,575 | 40,575 | Basic shelter kits |  |  |  |
|  |  |  | 20,000 | Vouchers for repair | 60,575 | Conditional cash-support for shelter |  |
|  | HH with lightly damaged housing | 27,068 | 10,000 | Shelter repair (seal-off) kits |  |  |  |
|  |  |  | 17,068 | Basic shelter kits |  |  |  |
|  | SUBTOTAL | 101,657 |  |  |  |  |  |
| TOTAL CASELOAD | 127,147 |  |  |  |  |  |

Technical Standards and Intervention Types – SAMPLE ONLY